## Activities
ID | Duration | Predecessors | Task | Resource Name
1 | 30 |  | Create a temporary support | Manlift, Manlift Driver
2 | 99.4 |  | Move 'Stiffener1_2UPN' | Forklift, Forklift Driver, Worker
3 | 93.7 |  | Move 'Stiffener1_3UPN' | Forklift, Forklift Driver, Worker
4 | 103.7 |  | Move 'Frame1 Connection over' | Forklift, Forklift Driver, Worker
5 | 98 |  | Move 'Stiffener1_4UPN' | Forklift, Forklift Driver, Worker
6 | 92.8 |  | Move 'Stiffener1_1UPN' | Forklift, Forklift Driver, Worker
7 | 103.5 |  | Move 'Frame1 Connection Under' | Forklift, Forklift Driver, Worker
8 | 107.9 |  | Move 'Frame1 Plate4' | Forklift, Forklift Driver, Worker
9 | 99.8 |  | Move 'Frame1 Plate1' | Forklift, Forklift Driver, Worker
10 | 30 |  | Create a temporary support | Manlift, Manlift Driver
11 | 109.4 |  | Move 'Frame1Plate2' | Forklift, Forklift Driver, Worker
12 | 30 |  | Create a temporary support | Manlift, Manlift Driver
13 | 102.6 |  | Move 'Frame1Plate3' | Forklift, Forklift Driver, Worker
14 | 30 |  | Brace 'CoreWall_2_side2' | Crane, Crane Driver, Worker
15 | 30 |  | Brace 'CoreWall_1_side2' | Crane, Crane Driver, Worker
16 | 30 |  | Brace 'CoreWall_2_side1' | Crane, Crane Driver, Worker
17 | 30 |  | Brace 'CoreWall_1_side1' | Crane, Crane Driver, Worker
18 | 91.4 | 16, 17, 14, 15 | Move 'MainBeam1_HEA' | Forklift, Forklift Driver, Worker
19 | 120 | 18 | Slice 'MainBeam1_HEA' | Slicer
20 | 83.2 | 16, 17, 14, 19, 15 | Move 'MainBeam1_HEA_0' | Forklift, Forklift Driver, Worker
21 | 83.7 | 16, 17, 14, 19, 15 | Move 'MainBeam1_HEA_1' | Forklift, Forklift Driver, Worker
22 | 105.9 | 16, 17, 14, 15 | Move 'CoreWall_2_internal' | Forklift, Forklift Driver, Worker
23 | 56.1 | 22, 16, 17, 14, 15 | Move 'CoreWall_2_internal' | Forklift, Forklift Driver, Worker
24 | 120 | 23, 22 | Slice 'CoreWall_2_internal' | Slicer
25 | 4.1 | 16, 17, 24, 14, 15 | Move 'CoreWall_2_internal_0' | Forklift, Forklift Driver, Worker
26 | 120 | 24 | Slice 'CoreWall_2_internal_1' | Slicer
27 | 2.2 | 26, 16, 17, 14, 15 | Move 'CoreWall_2_internal_1_0' | Forklift, Forklift Driver, Worker
28 | 120 | 26 | Slice 'CoreWall_2_internal_1_1' | Slicer
29 | 2.5 | 28, 16, 17, 14, 15 | Move 'CoreWall_2_internal_1_1_1' | Forklift, Forklift Driver, Worker
30 | 120 | 28, 29 | Slice 'CoreWall_2_internal_1_1_1' | Slicer
31 | 2.9 | 16, 17, 14, 30, 15 | Move 'CoreWall_2_internal_1_1_1_1' | Forklift, Forklift Driver, Worker
32 | 120 | 30, 31 | Slice 'CoreWall_2_internal_1_1_1_1' | Slicer
33 | 3.2 | 32, 16, 17, 14, 15 | Move 'CoreWall_2_internal_1_1_1_1_1' | Forklift, Forklift Driver, Worker
34 | 120 | 32, 33 | Slice 'CoreWall_2_internal_1_1_1_1_1' | Slicer
35 | 60.1 | 16, 17, 34, 14, 15 | Move 'CoreWall_2_internal_1_1_1_1_1_0' | Forklift, Forklift Driver, Worker
36 | 63.6 | 16, 17, 34, 14, 15 | Move 'CoreWall_2_internal_1_1_1_1_1_1' | Forklift, Forklift Driver, Worker
37 | 120 | 32 | Slice 'CoreWall_2_internal_1_1_1_1_0' | Slicer
38 | 53.2 | 37, 16, 17, 14, 15 | Move 'CoreWall_2_internal_1_1_1_1_0_0' | Forklift, Forklift Driver, Worker
39 | 56.2 | 37, 16, 17, 14, 15 | Move 'CoreWall_2_internal_1_1_1_1_0_1' | Forklift, Forklift Driver, Worker
40 | 2 | 37, 16, 17, 14, 39, 15 | Move 'CoreWall_2_internal_1_1_1_1_0_1' | Forklift, Forklift Driver, Worker
41 | 120 | 30 | Slice 'CoreWall_2_internal_1_1_1_0' | Slicer
42 | 45.9 | 41, 16, 17, 14, 15 | Move 'CoreWall_2_internal_1_1_1_0_0' | Forklift, Forklift Driver, Worker
43 | 49.1 | 41, 16, 17, 14, 15 | Move 'CoreWall_2_internal_1_1_1_0_1' | Forklift, Forklift Driver, Worker
44 | 120 | 28 | Slice 'CoreWall_2_internal_1_1_0' | Slicer
45 | 36.4 | 44, 16, 17, 14, 15 | Move 'CoreWall_2_internal_1_1_0_0' | Forklift, Forklift Driver, Worker
46 | 40.6 | 44, 16, 17, 14, 15 | Move 'CoreWall_2_internal_1_1_0_1' | Forklift, Forklift Driver, Worker
47 | 120 | 26, 27 | Slice 'CoreWall_2_internal_1_0' | Slicer
48 | 29.3 | 47, 16, 17, 14, 15 | Move 'CoreWall_2_internal_1_0_0' | Forklift, Forklift Driver, Worker
49 | 32.8 | 47, 16, 17, 14, 15 | Move 'CoreWall_2_internal_1_0_1' | Forklift, Forklift Driver, Worker
50 | 120 | 25, 24 | Slice 'CoreWall_2_internal_0' | Slicer
51 | 20.7 | 50, 16, 17, 14, 15 | Move 'CoreWall_2_internal_0_0' | Forklift, Forklift Driver, Worker
52 | 26.1 | 50, 16, 17, 14, 15 | Move 'CoreWall_2_internal_0_1' | Forklift, Forklift Driver, Worker
53 | 101.8 | 16, 17, 14, 15 | Move 'CoreWall_2_external' | Forklift, Forklift Driver, Worker
54 | 120 | 53 | Slice 'CoreWall_2_external' | Slicer
55 | 2.3 | 16, 54, 17, 14, 15 | Move 'CoreWall_2_external_1' | Forklift, Forklift Driver, Worker
56 | 120 | 54 | Slice 'CoreWall_2_external_0' | Slicer
57 | 2.7 | 56, 16, 17, 14, 15 | Move 'CoreWall_2_external_0_1' | Forklift, Forklift Driver, Worker
58 | 120 | 56 | Slice 'CoreWall_2_external_0_0' | Slicer
59 | 2.3 | 58, 16, 17, 14, 15 | Move 'CoreWall_2_external_0_0_0' | Forklift, Forklift Driver, Worker
60 | 120 | 58, 59 | Slice 'CoreWall_2_external_0_0_0' | Slicer
61 | 3.4 | 16, 17, 14, 60, 15 | Move 'CoreWall_2_external_0_0_0_0' | Forklift, Forklift Driver, Worker
62 | 120 | 54, 55 | Slice 'CoreWall_2_external_1' | Slicer
63 | 42.6 | 16, 62, 17, 14, 15 | Move 'CoreWall_2_external_1_0' | Forklift, Forklift Driver, Worker
64 | 58.6 | 16, 62, 17, 14, 15 | Move 'CoreWall_2_external_1_1' | Forklift, Forklift Driver, Worker
65 | 120 | 57, 56 | Slice 'CoreWall_2_external_0_1' | Slicer
66 | 38.6 | 16, 17, 14, 65, 15 | Move 'CoreWall_2_external_0_1_0' | Forklift, Forklift Driver, Worker
67 | 54 | 16, 17, 14, 65, 15 | Move 'CoreWall_2_external_0_1_1' | Forklift, Forklift Driver, Worker
68 | 120 | 58 | Slice 'CoreWall_2_external_0_0_1' | Slicer
69 | 32.2 | 16, 68, 17, 14, 15 | Move 'CoreWall_2_external_0_0_1_0' | Forklift, Forklift Driver, Worker
70 | 48.5 | 16, 68, 17, 14, 15 | Move 'CoreWall_2_external_0_0_1_1' | Forklift, Forklift Driver, Worker
71 | 120 | 60 | Slice 'CoreWall_2_external_0_0_0_1' | Slicer
72 | 28.2 | 71, 16, 17, 14, 15 | Move 'CoreWall_2_external_0_0_0_1_0' | Forklift, Forklift Driver, Worker
73 | 45.8 | 71, 16, 17, 14, 15 | Move 'CoreWall_2_external_0_0_0_1_1' | Forklift, Forklift Driver, Worker
74 | 120 | 61, 60 | Slice 'CoreWall_2_external_0_0_0_0' | Slicer
75 | 27.8 | 16, 17, 14, 74, 15 | Move 'CoreWall_2_external_0_0_0_0_0' | Forklift, Forklift Driver, Worker
76 | 41.3 | 16, 17, 14, 74, 15 | Move 'CoreWall_2_external_0_0_0_0_1' | Forklift, Forklift Driver, Worker
77 | 0.1 | 16, 17, 14, 74, 76, 15 | Move 'CoreWall_2_external_0_0_0_0_1' | Forklift, Forklift Driver, Worker
78 | 1.3 | 16, 77, 17, 14, 74, 76, 15 | Move 'CoreWall_2_external_0_0_0_0_1' | Forklift, Forklift Driver, Worker
79 | 1.1 | 78, 16, 77, 17, 14, 74, 76, 15 | Move 'CoreWall_2_external_0_0_0_0_1' | Forklift, Forklift Driver, Worker
80 | 76.5 | 16, 14, 17, 15 | Move 'CoreWall_2_side2' | Forklift, Forklift Driver, Worker
81 | 120 | 14, 80 | Slice 'CoreWall_2_side2' | Slicer
82 | 33.1 | 81, 16, 17, 15 | Move 'CoreWall_2_side2_0' | Forklift, Forklift Driver, Worker
83 | 26.2 | 81, 16, 17, 15 | Move 'CoreWall_2_side2_1' | Forklift, Forklift Driver, Worker
84 | 113 | 16, 17, 15 | Move 'CoreWall_2_side1' | Forklift, Forklift Driver, Worker
85 | 120 | 16, 84 | Slice 'CoreWall_2_side1' | Slicer
86 | 34 | 85, 17, 15 | Move 'CoreWall_2_side1_1' | Forklift, Forklift Driver, Worker
87 | 26.2 | 85, 17, 15 | Move 'CoreWall_2_side1_0' | Forklift, Forklift Driver, Worker
88 | 30 |  | Brace 'CoreWall_1_internal' | Crane, Crane Driver, Worker

## Resources
Resource Name | Cost
Forklift | 50
Forklift Driver | 30
Worker | 20
Slicer | 100
Crane | 75
Crane Driver | 35
Manlift | 40
Manlift Driver | 25